## Sheet1
Sr.No. | Module | Task
1. | Enter Action Plan | Need to create table and store procedure for show data.
Need to create page in which data will be show and enter data accordingly.
Need to create store procedure for insert data.
2. | Update Action Plan | Need to create table and store procedure for show data.
Need to create page in which data will be show and enter data accordingly.
Need to create store procedure for Update data.
3. | Notification for Enter Action Plan | Need to insert "Action plan data" to notification tables by store procedure.
Need to create logic for show notification count on the frant fo page.
Need to create page for show action plan data and update status(Approve & Reject).
Reflect status at "Enter action plan" page and control do enable & disable accordingly status.
4. | Notification for Update Action Plan | Need to insert "Update plan data" to notification tables.
Need to create logic for show notification count on the frant fo page.
Need to create page for show "update action plan" data and update status(Approve & Reject).
Reflect status at "Update action plan" page and control do enable & disable accordingly status.
5. | Tesing | Tesing for all module.

## Sheet2
10/15/2019
Project | What all things to do | Est. Time | Work Started | Status | Expected Closure | Other Plan | Challenges | Help required | Execution Gap | Delivered By
Tata motors (CPSC) | Done new changes at Adherence notification alert | 4 H | 10/15/2019 | Completed | 10/15/2019 | Nothing | Nothing | No | No | Snehaj
Tata motors (CPSC) | Done new changes at Desired (After sale) notification alert | 4 H | 10/15/2019 | Completed | 10/15/2019 | Nothing | Nothing | No | No | Snehaj
Tata motors (CPSC) | Validation are not working at Action plan module | 1:30 H | 9/30/2019 | Completed | 9/30/2019 | Nothing | Nothing | No | No | Monika
Tata motors (CPSC) | Need to create action plan mudole at old tata motors project. Then i am understading old product table structure and coding, in which adjust new code at exists pages. | 5.30 H | 9/30/2019 | In Process | 10/30/2017 | Nothing | Adjust new module with exists pages and database tables. | Snehaj | No | Snehaj

## Sheet3
11-14-2019
Project | What all things to do | Est. Time | Work Started | Status | Expected Closure | Other Plan | Challenges | Help required | Execution Gap | Delivered By
Tata motors (CPSC) | Creating Update action plan at Tata cpsc | 8 H | 11-14-2019 | Completed | 11-21-2019 | Nothing | Nothing | No | No | Snehaj
Tata motors (CPSC) | Remove decimal point to Max point and ParascoreRYG. | 4 H | 2019-12-11 | Completed | 2019-12-11 | Nothing | Nothing | No | No | Snehaj
10/18/2019
Project | What all things to do | Est. Time | Work Started | Status | Expected Closure | Other Plan | Challenges | Help required | Execution Gap | Delivered By
Tata motors (CPSC) | Creating new page of Adherence Sale | 4 H | 10/18/2019 | Completed | 10/18/2019 | Nothing | Nothing | No | No | Snehaj
Tata motors (CPSC) | Creating new page of Desired Sale | 4 H | 10/18/2019 | Completed | 10/18/2019 | Nothing | Nothing | No | No | Snehaj